## Sprint Overview
EDT - Sprint Task Tracker
RAG-Based Persona-Driven Itinerary System ¦ Updated: 2 Mar 2026
# | Sprint | Category | Task | Status | Trello List
1 | Sprint 1 | Backend | Anonymous Device Session API | Done | Done Sprint DATE - DATE 🎉
2 | Sprint 1 | Backend | Implement Itinerary Fetch APIs | Done | Done Sprint DATE - DATE 🎉
3 | Sprint 1 | Backend | POI Data Import from Overture Maps | Done | Done Sprint DATE - DATE 🎉
4 | Sprint 1 | Backend | POI Vector Search API | Done | Done Sprint DATE - DATE 🎉
5 | Sprint 1 | Backend | Run Database Migrations on Cloud SQL | Done | Done Sprint DATE - DATE 🎉
6 | Sprint 1 | Backend | Set up Cloud SQL PostgreSQL with pgvector | Done | Done Sprint DATE - DATE 🎉
7 | Sprint 1 | Backend | Trip Draft Save/Resume API | Done | Done Sprint DATE - DATE 🎉
8 | Sprint 1 | DevOps | Deploy FastAPI to Cloud Run | Done | Done Sprint DATE - DATE 🎉
9 | Sprint 1 | Frontend | Flutter App - Trip Planning Screen | Done | Done Sprint DATE - DATE 🎉
10 | Sprint 1 | General | Basic Dummy APIs to be Set up | Done | Done Sprint DATE - DATE 🎉
11 | Sprint 1 | General | Basic UI Elements for Mobile App for Both iOS and Android | Done | Done Sprint DATE - DATE 🎉
12 | Sprint 1 | General | Cloud Run Set Up | Done | Done Sprint DATE - DATE 🎉
13 | Sprint 1 | General | First Version of Design Pages | Done | Done Sprint DATE - DATE 🎉
14 | Sprint 1 | General | Vector DB Set up | Done | Done Sprint DATE - DATE 🎉
15 | Sprint 1 | QA/Testing | API Integration Tests | Done | Done Sprint DATE - DATE 🎉
16 | Sprint 2 | Backend | Multi-City Trip Support | Done | Done Sprint DATE - DATE 🎉
17 | Sprint 2 | Backend | Wishlist API | Done | Done Sprint DATE - DATE 🎉
18 | Sprint 2 | DevOps | CI/CD Pipeline Setup | In Dev | Dev
19 | Sprint 2 | Frontend | Preference Persistence (AsyncStorage) | Done | Done Sprint DATE - DATE 🎉
20 | Sprint 2 | Frontend | Trip Draft Auto-Save and Resume Banner | Done | Done Sprint DATE - DATE 🎉
21 | Sprint 2 | Frontend | Wishlist UI and Heart Toggle | Done | Done Sprint DATE - DATE 🎉
22 | Sprint 2 | General | EDA exploration for Itinerary and Persona Match | In Dev | Dev
23 | Sprint 3 | Backend | Country Planner — Multi-city day allocation with constraint satisfaction | Next Sprint | Next Sprint
24 | Sprint 3 | Backend | Itinerary Generator — RAG pipeline for day-wise trip assembly | Next Sprint | Next Sprint
25 | Sprint 3 | Crawling | Reviews & Tips Ingestion — Scrape and normalize user reviews | Next Sprint | Next Sprint
26 | Sprint 3 | Frontend | Map Integration — Interactive map showing POI markers per day | Next Sprint | Next Sprint
27 | Sprint 3 | Frontend | Timeline View — Day-by-day itinerary with activity cards and transit connectors | Next Sprint | Next Sprint
28 | Sprint 3 | Frontend | Flutter App - Itinerary View | Done | Done Sprint DATE - DATE 🎉
29 | Sprint 3 | Knowledge Graph | Simple Sequencing — Knowledge graph edges for visit ordering | Next Sprint | Next Sprint
30 | Sprint 3 | QA/Testing | AI Output Validation — Itinerary quality checks and edge case tests | Next Sprint | Next Sprint
31 | Sprint 3 | Sprint Goal | Sprint Goal: E2E Itinerary Flow with one country and, mobile app, and data craweled to VD | In Dev | Dev
32 | Sprint 3 | Sprint Goal | Sprint Goal: First AI Itinerary — User sees a full day-wise trip | Next Sprint | Next Sprint
33 | Sprint 3 | Vector DB | Relevance Ranking — Persona-aware POI scoring with pgvector | Next Sprint | Next Sprint
34 | Backlog | Backend | Admin Panel - POI Management | Backlog | Backlog
35 | Backlog | Backend | Analytics Dashboard - Usage Metrics | Backlog | Backlog
36 | Backlog | Backend | Booking Integration | Backlog | Backlog
37 | Backlog | Backend | Google Places API Integration | Sprint Backlog | Sprint Backlog
38 | Backlog | Backend | LLM-Powered POI Scoring | Backlog | Backlog
39 | Backlog | Backend | Push Notifications Service | Backlog | Backlog
40 | Backlog | Backend | Rate Limiting and API Security | Backlog | Backlog
41 | Backlog | Backend | User Authentication with Firebase Auth | Backlog | Backlog
42 | Backlog | Backend | Weather-Aware Itinerary Adjustments | Sprint Backlog | Sprint Backlog
43 | Backlog | Frontend | AI Chat Assistant for Trip Planning | Sprint Backlog | Sprint Backlog
44 | Backlog | Frontend | Accessibility (a11y) Compliance | Backlog | Backlog
45 | Backlog | Frontend | Budget Tracker | Backlog | Backlog
46 | Backlog | Frontend | Flutter App - Onboarding Flow | Backlog | Backlog
47 | Backlog | Frontend | Itinerary Customization - Swap/Remove POIs | Sprint Backlog | Sprint Backlog
48 | Backlog | Frontend | Offline Mode - Download Itinerary | In Dev | Dev
49 | Backlog | Frontend | Real-time Navigation Integration | Backlog | Backlog
50 | Backlog | Sprint Goal | Sprint Goal: -Infra Set up and First version of E2E Flow | Done | Done Sprint DATE - DATE 🎉

## Sprint Summary
Sprint Summary Dashboard
Sprint | Duration | Goal | Total Tasks | Done
Sprint 1 | 2 Weeks | User can start exploring and create a trip draft | 15 | 15/15
Sprint 2 | 2 Weeks | System understands who the traveler is and what they want | 7 | 5/7
Sprint 3 | 2 Weeks | First AI itinerary — user sees a full day-wise trip | 9 | 1/9
Category Breakdown
Category | Sprint 1 | Sprint 2 | Sprint 3 | Total
Backend | 7 | 2 | 2 | 11
Crawling |  |  | 1 | 1
DevOps | 1 | 1 |  | 2
Frontend | 1 | 3 | 3 | 7
General | 5 | 1 |  | 6
Knowledge Graph |  |  | 1 | 1
QA/Testing | 1 |  | 1 | 2
Vector DB |  |  | 1 | 1

## Sprint 1
Sprint 1 — Task Details
# | Category | Task | Status
1 | Backend | Anonymous Device Session API | Done
2 | Backend | Implement Itinerary Fetch APIs | Done
3 | Backend | POI Data Import from Overture Maps | Done
4 | Backend | POI Vector Search API | Done
5 | Backend | Run Database Migrations on Cloud SQL | Done
6 | Backend | Set up Cloud SQL PostgreSQL with pgvector | Done
7 | Backend | Trip Draft Save/Resume API | Done
8 | DevOps | Deploy FastAPI to Cloud Run | Done
9 | Frontend | Flutter App - Trip Planning Screen | Done
10 | General | Basic Dummy APIs to be Set up | Done
11 | General | Basic UI Elements for Mobile App for Both iOS and Android | Done
12 | General | Cloud Run Set Up | Done
13 | General | First Version of Design Pages | Done
14 | General | Vector DB Set up | Done
15 | QA/Testing | API Integration Tests | Done

## Sprint 2
Sprint 2 — Task Details
# | Category | Task | Status
1 | Backend | Multi-City Trip Support | Done
2 | Backend | Wishlist API | Done
3 | DevOps | CI/CD Pipeline Setup | In Dev
4 | Frontend | Preference Persistence (AsyncStorage) | Done
5 | Frontend | Trip Draft Auto-Save and Resume Banner | Done
6 | Frontend | Wishlist UI and Heart Toggle | Done
7 | General | EDA exploration for Itinerary and Persona Match | In Dev

## Sprint 3
Sprint 3 — Task Details
Goal: E2E Itinerary Flow with one country and, mobile app, and data craweled to VD
# | Category | Task | Status
1 | Backend | Country Planner — Multi-city day allocation with constraint satisfaction | Next Sprint
2 | Backend | Itinerary Generator — RAG pipeline for day-wise trip assembly | Next Sprint
3 | Crawling | Reviews & Tips Ingestion — Scrape and normalize user reviews | Next Sprint
4 | Frontend | Map Integration — Interactive map showing POI markers per day | Next Sprint
5 | Frontend | Timeline View — Day-by-day itinerary with activity cards and transit connectors | Next Sprint
6 | Frontend | Flutter App - Itinerary View | Done
7 | Knowledge Graph | Simple Sequencing — Knowledge graph edges for visit ordering | Next Sprint
8 | QA/Testing | AI Output Validation — Itinerary quality checks and edge case tests | Next Sprint
9 | Vector DB | Relevance Ranking — Persona-aware POI scoring with pgvector | Next Sprint